AZURESKY PTY LTD (T1159)

# TECHNICAL SIGNATORY
CONTINUITY & QMS RISK ASSESSMENT

Loss of one Technical Signatory and continuity of accredited laboratory operations

| Document control | Details |
| --- | --- |
| Document reference | AS-QMS-RISK-TS-01 |
| Document owner | Laboratory Manager / Quality Management Representative (as assigned) |
| Prepared | October 2026 |
| Review trigger | December 2026 SANAS assessment; material change; TS availability or approval status change |
| Status | Draft for management review and approval |
| Related documents | ISO/IEC 17025:2017; SANAS R 03-10; SANAS R 51-10; applicable SANAS Terms and Conditions; internal QMS procedures |

This assessment is an internal risk-management record. It does not replace SANAS requirements, formal notification where required, or approval of a proposed Technical Signatory / Contracted Technical Signatory.

# 1. Purpose

This assessment records the risks arising from the departure of one of Azuresky’s two previously available Technical Signatories (TS). The laboratory currently has one remaining TS, who is the Laboratory Manager. The purpose is to demonstrate that management has considered the effect on technical authorisation, result validity, impartiality, workload, management-system effectiveness, client service and continuity of accredited activities, and has established controls and a time-bound recovery plan.

The assessment is forward-looking and is intended to support preparation for the SANAS assessment expected in December 2026. It must be reviewed when assumptions change and supported by objective records showing that planned controls have been implemented.

# 2. Scope and current situation

The laboratory has lost one of its two Technical Signatories and currently relies on the Laboratory Manager as the sole SANAS-approved TS.

A new Supervisor with extensive industry experience has been appointed. The Supervisor is learning Azuresky’s QMS, procedures, records, reporting controls and workplace practices, with a view to applying for SANAS TS approval.

Two additional Operators and one Analyst have been appointed to reduce the Laboratory Manager’s involvement in sample preparation and routine supervision, allowing more time for technical oversight and QMS maintenance.

The current target is to have the Supervisor assessed for TS approval during the first quarter of 2027. This is a target only; approval depends on the applicable SANAS application and evaluation process.

Until the Supervisor is formally approved for the relevant scope, accredited reports must be authorised by the currently approved TS, subject to the laboratory’s documented review and release procedure.

A specific contingency is required for annual leave, sickness, resignation or other unavailability of the sole approved TS.

# 3. Reference requirements and implications

| Reference | Source requirement / principle | Application to this risk assessment |
| --- | --- | --- |
| SANAS R 03-10, 3.1 and 3.2 | Personnel must be competent for assigned tasks; signatories to reports must be approved. Lack of appropriately qualified and competent personnel may result in failure to obtain or loss of accreditation. | Maintain competence records and ensure only approved signatories authorise reports under accreditation. |
| SANAS R 03-10, 4.4.3 | The nominated representative must have authority to ensure the management system is implemented and followed, including ensuring released results are authorised by an approved signatory. | Confirm the NR / accreditation contact, authority, access to top management and clear QMS ownership. |
| SANAS R 03-10, 4.4.5 | Significant changes relevant to accreditation should be notified in writing at least four weeks before taking effect; an unexpected occurrence materially affecting the CAB’s ability to meet its obligations requires prompt written notification no later than 24 hours after the occurrence. | Management must document its decision on SANAS notification and act promptly if the event materially affects accredited capability. Verify the appropriate notification with the SANAS Accreditation Manager. |
| SANAS R 03-10, 5.1.1 | A TS accepts responsibility for report contents, needs current method competence, must assess and interpret data, evaluate deviations, and be satisfied required checks are complete. | Use a documented technical review and release checklist; do not treat the signature as an administrative step. |
| SANAS R 03-10, 5.2.1–5.2.3 | A CTS is an interim arrangement following an unexpected situation without an approved TS; the period may not exceed 18 months. SANAS must be informed of the intent to obtain CTS approval and the CAB must maintain a formal agreement, competence evidence, sufficient presence, test reconstruction / repetition arrangements and documented procedures/records. | Use a CTS as a controlled contingency if necessary, following SANAS engagement and the required approval/arrangements. Do not assume a contractor may sign accredited reports before the applicable approval is confirmed. |
| SANAS R 03-10, 6.1–6.5 | Applications require the relevant application, current CV and declarations of competence; SANAS may evaluate by interview, witnessing, records or a combination. | Build a complete application package and allow time for SANAS evaluation; the Q1 2027 target is not a guaranteed approval date. |
| SANAS R 51-10, 4.1.1 | Loss of all technical signatories is identified as a reason for voluntary suspension, alongside other circumstances that compromise result integrity or compliance. | One TS remains, so the loss-of-all-TS trigger is not automatically met. However, management must assess whether the actual circumstances materially compromise accredited capability and consult SANAS where needed. |
| SANAS R 51-10, 7.1–7.3 and 8.1.3 | If accreditation is suspended, use of the accreditation symbol/references must cease for the affected status/scope; affected clients must be informed without delay. Following loss of all TS, suspension continues until SANAS verifies a new proposed TS for relevant scope(s). | Maintain a documented stop-work / report-control plan in case SANAS suspends or restricts accreditation; do not imply that a new employee automatically restores signatory capacity. |

# 4. Risk assessment method

The ratings below are qualitative and are intended to prioritise action. Azuresky should align the scale with its approved risk procedure if a formal corporate matrix already exists.

| Rating | Likelihood | Impact |
| --- | --- | --- |
| 1 | Rare | Negligible; no material effect on result validity or compliance |
| 2 | Unlikely | Minor; manageable through routine controls |
| 3 | Possible | Moderate; may cause delay, rework or a limited control failure |
| 4 | Likely | Major; credible risk to release controls, QMS effectiveness or client commitments |
| 5 | Almost certain | Critical; likely to compromise accredited reporting, result validity or continuity |

Risk score = Likelihood × Impact. Suggested interpretation: 1–4 Low; 5–9 Moderate; 10–16 High; 17–25 Critical. Initial and residual scores are management estimates and must be reviewed against evidence.

# 5. Risk register

| ID | Risk / cause | Initial risk | Potential consequence | Controls / actions | Owner | Status | Residual target |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | Sole TS unavailable through annual leave, illness, resignation or emergency | 4 × 5 = 20 Critical | No authorised person available to release accredited reports; delayed service; pressure to release without appropriate authorisation. | Do not release reports under accreditation without an approved signatory. Before planned leave, arrange an approved CTS or another formally approved TS where appropriate; engage SANAS in advance. For unexpected absence, hold affected reports and contact the SANAS Accreditation Manager promptly for direction. Document client communication and backlog control. | CEO / Lab Manager | Open until tested and documented | Target residual: 2 × 5 = 10 (High) |
| R2 | New Supervisor not yet approved as TS | 4 × 5 = 20 Critical | Internal experience/training may be mistaken for SANAS approval; unauthorised accredited reporting could undermine confidence and compliance. | Supervisor may train, review and prepare technical records only within demonstrated competence and delegated authority. Maintain a competency matrix, training records, observed work, method-specific evaluations and signed declaration of competence. Keep accredited report authorisation with current approved TS until formal approval for the relevant scope is confirmed. | Lab Manager / Supervisor | In progress | Target residual: 2 × 5 = 10 (High) |
| R3 | Workload concentration on the remaining TS | 4 × 4 = 16 High | Delayed reviews, fatigue, missed checks, reduced time for internal audits, corrective actions, management review and oversight. | Use the two Operators and Analyst to absorb appropriate preparation and analytical workload after competence authorisation. Establish daily workload allocation, a report-review queue, leave planning and protected weekly QMS/technical oversight time. Monitor overdue reports, overtime, errors and open QMS actions. | Lab Manager / Supervisor | In progress | Target residual: 2 × 4 = 8 (Moderate) |
| R4 | Result released without adequate technical review or with unresolved deviation | 3 × 5 = 15 High | Invalid or unreliable result; client harm; complaint; nonconformity; accreditation risk. | Use a controlled pre-release checklist covering sample identity/traceability, method and scope, calculations, QC/CRM checks, equipment status, deviations, uncertainty/reporting rules where applicable, transcription/export integrity and authorisation. Hold reports with unresolved exceptions. Retain review evidence. | Approved TS / Analyst | To verify | Target residual: 1 × 5 = 5 (Moderate) |
| R5 | CTS contingency not available or not established in time | 3 × 5 = 15 High | Planned leave or prolonged absence interrupts accredited report authorisation. | Identify suitable candidate(s) early; verify method/scope competence and availability; obtain SANAS guidance and approval as applicable; execute written agreement covering confidentiality, conflict of interest, responsibilities, presence, test reconstruction/repetition and competence review. Keep proof of competence at the laboratory. | CEO / Lab Manager | Open | Target residual: 2 × 5 = 10 (High) |
| R6 | SANAS not notified where required, or notification is delayed | 3 × 5 = 15 High | Failure to meet SANAS requirements; increased risk of suspension or adverse assessment finding. | Record the date management became aware of the departure, its impact assessment and notification decision. Review R 03-10 clause 4.4.5 and consult the Accreditation Manager. Where the event materially affects the CAB’s ability to meet accreditation obligations, ensure written notification within the stated 24-hour period. Retain correspondence and response. | CEO / Nominated Representative | Immediate verification required | Target residual: 1 × 5 = 5 (Moderate) |
| R7 | QMS activities deteriorate while management focuses on production | 4 × 4 = 16 High | Overdue internal audits, corrective actions, equipment maintenance, competency reviews, document control or management review inputs. | Assign a named owner and due date for each QMS process. Supervisor supports day-to-day monitoring; Lab Manager retains defined technical responsibilities; CEO provides resources and escalation authority. Maintain a weekly QMS action tracker and escalate overdue high-risk items. | CEO / Lab Manager / Supervisor | In progress | Target residual: 2 × 4 = 8 (Moderate) |
| R8 | New Operators / Analyst work beyond authorised competence | 3 × 4 = 12 High | Incorrect preparation/testing, uncontrolled calculations, poor traceability or repeat work. | Create task-specific authorisation matrix; conduct induction, supervised practice, witnessed demonstrations and competency sign-off before independent work. Keep training and authorisation records current; perform ongoing monitoring and periodic reassessment. | Supervisor / Lab Manager | In progress | Target residual: 1 × 4 = 4 (Low) |
| R9 | Client expectations not managed during delayed authorisation | 3 × 3 = 9 Moderate | Late delivery, complaints, commercial pressure to bypass controls or unclear status of results. | Set realistic turnaround times; communicate delays without implying unapproved results are accredited. Keep a log of affected jobs, client updates, commitments and final disposition. Do not use commercial urgency to bypass review or authorisation. | Lab Manager / Client contact | To implement | Target residual: 1 × 3 = 3 (Low) |
| R10 | Accreditation status or scope represented incorrectly if suspension/reduction occurs | 2 × 5 = 10 High | Reports or materials may incorrectly display the SANAS symbol or claim accreditation for affected activities. | Maintain a written escalation and communication plan. If SANAS suspends, reduces, withdraws or accreditation expires, follow the exact scope/status conditions; immediately stop use of accreditation references/symbols where required and inform affected clients without delay. Control report templates and website/marketing claims. | CEO / Nominated Representative / Document Controller | To document | Target residual: 1 × 5 = 5 (Moderate) |
| R11 | Application for new TS delayed or incomplete | 3 × 4 = 12 High | Single-person dependency continues beyond Q1 2027; CTS costs and operational pressure may persist. | Prepare current CV, qualification/experience evidence, method-specific competence declaration, training and evaluation records, scope requested and supporting records. Submit with sufficient lead time and track SANAS queries. Maintain CTS contingency until the new TS is formally approved. | Supervisor / Lab Manager / CEO | Planned | Target residual: 2 × 4 = 8 (Moderate) |
| R12 | Knowledge held by departing TS not retained | 3 × 3 = 9 Moderate | Loss of tacit knowledge, historical decisions, technical interpretation and recurring problem awareness. | Capture available handover records, method notes, technical decisions, open deviations, client-specific requirements and recurring equipment/QC issues. Restrict access appropriately and keep records in controlled repositories. | Lab Manager / Supervisor | To verify | Target residual: 1 × 3 = 3 (Low) |

# 6. Operational continuity plan

## 6.1 Normal operations while one approved TS remains

The Laboratory Manager remains the sole approved TS and authorises reports within the scope for which that person is approved.

No report is to be released as accredited solely on the basis that the Supervisor has industry experience, has completed internal training, or is expected to be assessed by SANAS.

The laboratory will continue to accept and perform work only where competent personnel, equipment, methods, quality controls and review capacity are available. Work that cannot be controlled adequately must be delayed, declined or otherwise managed under the relevant QMS procedure.

Routine analytical work may be performed by authorised Operators and the Analyst within their documented competence. The TS remains responsible for the report authorisation decision and must have enough evidence to make that decision.

A weekly review will check outstanding reports, QC exceptions, nonconforming work, equipment status, complaints, staff competence, internal audit actions and other high-risk QMS tasks.

## 6.2 Annual leave, illness or other absence of the sole TS

The laboratory must not assume that a report can be issued under accreditation merely because testing was completed before the TS went on leave. The following decision path applies:

Before planned leave, the CEO and Lab Manager will review the leave dates, expected report volume, client commitments and whether an approved TS will be available for the full period.

Where accredited reports must be authorised during the absence, the preferred contingency is to arrange a suitable CTS or other SANAS-approved TS arrangement, with SANAS engagement and approval completed as applicable before the arrangement is relied upon.

For a CTS, complete the formal agreement and required controls under R 03-10 clause 5.2, including confidentiality, conflict of interest, responsibility for authorisations, proof of competence, sufficient presence, specified test repetition/reconstruction and regular review of the competence of personnel performing the work.

If no approved signatory arrangement is in place, do not release reports under accreditation without appropriate authorisation. Hold reports securely, advise affected clients of realistic turnaround times and maintain sample/result traceability. Any alternative reporting must be assessed against SANAS requirements, the laboratory’s scope and applicable client/legal requirements; it must not imply accredited status where this is not valid.

For sudden unavailability, the Lab Manager or CEO will immediately activate the contingency, assess the effect on the laboratory’s ability to meet accreditation requirements and contact the SANAS Accreditation Manager promptly where required. Record decisions, notifications, affected work and client communication.

The laboratory will not backdate authorisations or retrospectively present a report as having been authorised by a person who was not approved or did not perform the required review.

## 6.3 Supervisor development and TS application

| Stage / target | Required action | Evidence to retain | Accountable |
| --- | --- | --- | --- |
| October 2026 | Complete induction into QMS, scope, methods, reporting controls, impartiality/confidentiality, nonconforming work, complaints and corrective action processes. | Induction checklist; training plan; controlled-document acknowledgement. | Supervisor / Lab Manager |
| October–November 2026 | Complete method-by-method competency assessment for requested scope; observe and perform work under supervision; demonstrate calculations, interpretation, QC review, deviation evaluation and report review. | Competency matrix; witnessed assessments; records of observed work; authorisation limits. | Lab Manager / Supervisor |
| Before December 2026 assessment | Compile evidence pack and demonstrate implemented controls, not only planned actions. Review report authorisation and CTS contingency with management. | Risk register updates; action evidence; training/competency records; meeting minutes; SANAS correspondence. | CEO / Lab Manager / Supervisor |
| Q4 2026–Q1 2027 | Prepare and submit TS application with current CV, qualifications/experience evidence, method-specific competence declaration and supporting records. Confirm timing and required assessment route with SANAS. | Application copy; submission receipt; correspondence; outstanding-items tracker. | Supervisor / Lab Manager |
| Q1 2027 target | Make Supervisor available for SANAS evaluation, which may include interview, witnessing and/or review of competence records. Do not treat the target date as guaranteed approval. | SANAS evaluation records and written confirmation of approval and approved scope. | CEO / Lab Manager / Supervisor |
| After approval | Update authorised signatory list, report-release procedure, controlled templates and relevant staff instructions only after written approval/scope confirmation. Review this risk assessment. | Approval evidence; revised controlled records; communication/training; effectiveness review. | Lab Manager / Document Controller |

# 7. CEO management commitment and recovery plan

This section must be completed by the CEO. It is intended to record management’s specific decision, resource commitment and deadline for closing the single-TS dependency. General assurances such as “the matter will be addressed” are not sufficient; the plan should identify a route, accountable person, date and contingency.

## CEO statement and approved plan:

Chosen route to restore signatory resilience (e.g., progress the Supervisor’s TS application and/or establish an approved CTS contingency):

________________________________________________________________________________

Actions management will take in October–December 2026:

Actions and milestones for January–March 2027:

Annual leave / sickness coverage plan for the current TS, including the named contingency and the point by which it must be operational:

Budget and resources approved (application / assessment costs, CTS fees, training, time, staffing or other resources):

How the CEO will monitor progress and escalate delays:

Conditions that would trigger pausing affected work, client notification and/or urgent engagement with SANAS:

CEO name: ____________________________________    Signature: ____________________________________

Date: ____________________    Next review date: ____________________

# 8. Management responsibilities

| Role | Responsibilities under this plan |
| --- | --- |
| CEO / top management | Approve the risk response and resources; decide and document SANAS engagement with the relevant Accreditation Manager; ensure a credible leave/absence contingency; review progress and unresolved high risks; complete Section 7. |
| Laboratory Manager / current TS | Maintain authorised report release within approved scope; ensure technical review is effective; protect time for QMS oversight; monitor workload, exceptions, competence and report backlog; lead the TS application preparation. |
| New Supervisor | Learn and follow the QMS; support work allocation and supervision; build method-specific competence evidence; monitor operator/analyst competence and operational controls; do not sign accredited reports until formal approval for the relevant scope is confirmed. |
| Operators and Analyst | Perform only authorised tasks; follow current methods and records; promptly report deviations, QC failures, equipment issues and workload risks; do not bypass hold/release controls. |
| Nominated Representative / QMS owner (confirm name) | Maintain accreditation communication and change records; monitor QMS implementation, internal audits, corrective actions, document control and management review inputs; ensure relevant decisions and evidence are available for assessment. |

# 9. Evidence file for the December 2026 SANAS assessment

The following evidence should be available, current and consistent with actual practice. Tick off each item before the assessment.

- ☐ Approved risk assessment with initial ratings, controls, owners, due dates, residual risk and management review.

- ☐ Record of the TS departure, date identified, impact evaluation and documented decision on SANAS notification; copy of correspondence and SANAS response, where applicable.

- ☐ Current approved TS list and clear evidence that report authorisation is restricted to approved signatories and relevant scope.

- ☐ Examples of recent report review/release records, including evidence of QC review, calculation checks, handling of deviations and resolution of exceptions.

- ☐ Supervisor’s induction, training plan, competency matrix, witnessed work and method-specific competence records.

- ☐ Operator and Analyst authorisation/competence records and defined task boundaries.

- ☐ Workload and report-backlog monitoring, protected QMS time, staffing allocation and evidence of overdue actions being escalated.

- ☐ CTS contingency plan and, if pursued, candidate evaluation, SANAS engagement/approval evidence, signed agreement and required competence/control records.

- ☐ QMS action tracker covering internal audits, corrective actions, equipment maintenance/calibration, document control, complaints, nonconforming work and management review.

- ☐ CEO-approved recovery plan with dates, resources, named owners and a contingency if Q1 2027 TS approval is delayed.

- ☐ Evidence that report templates, accreditation references and client communications can be controlled if SANAS changes the laboratory’s accreditation status or scope.

- ☐ Management review/minutes showing that the risk and effectiveness of controls were discussed and decisions recorded.

# 10. Monitoring, review and escalation

| Indicator | Frequency | Escalation trigger / response | Owner |
| --- | --- | --- | --- |
| Reports awaiting TS authorisation / oldest pending report | Daily on working days | Any report exceeds agreed turnaround or accumulates because of signatory availability: inform Lab Manager and client contact; review capacity and contingency. | Lab Manager |
| TS availability and planned leave calendar | Monthly and before each leave period | Any period without an approved signatory arrangement: escalate to CEO before leave is approved; establish approved cover or plan to hold accredited reports. | CEO / Lab Manager |
| Supervisor TS application milestones | Fortnightly until submission; monthly thereafter | Any milestone slips or SANAS requests additional evidence: update recovery plan and activate/extend CTS contingency as needed. | Supervisor / Lab Manager |
| Competence and QC exceptions | Ongoing; formally reviewed monthly | Any unresolved competence gap, failed QC, repeated calculation/export issue or unreviewed deviation: hold affected work/reports and initiate applicable QMS process. | Lab Manager / Supervisor |
| QMS actions, audits, equipment and corrective actions | Weekly tracker; monthly management review | Overdue high-risk action or evidence of loss of system control: escalate to CEO, assign resources and document corrective action. | QMS owner / CEO |
| Overall risk and effectiveness of controls | Before December 2026 assessment; after any material change; quarterly until second TS approval | If controls are ineffective or accredited capability may be compromised, reassess immediately and consult SANAS as appropriate. | CEO / Lab Manager |

# 11. Residual risk and acceptance

The residual risk ratings in Section 5 are targets, not evidence that the risk has already been reduced. The sole-TS dependency remains a significant risk until an effective and documented contingency is available and the second signatory has been approved for the relevant scope, or management has otherwise established a demonstrably compliant arrangement.

Management may accept only risks that remain within the organisation’s approved risk-acceptance criteria and where required controls are implemented. Any risk that could affect the laboratory’s ability to meet accreditation requirements, authorise results properly or produce reliable results must be escalated promptly. If the laboratory cannot maintain the required controls, it must not continue to issue affected reports as accredited merely to preserve turnaround time.

| Review decision | Complete after review |
| --- | --- |
| Are current accredited activities still supported by competent personnel, equipment, methods, QC and effective approved-signatory review? | ☐ Yes ☐ No ☐ Partially — details: __________________________ |
| Has management assessed and documented whether SANAS notification is required and completed it where required? | ☐ Yes ☐ No ☐ Not applicable with justification: ______________ |
| Is an effective, SANAS-compliant plan in place for the sole TS’s planned/unplanned absence? | ☐ Yes ☐ No ☐ In progress — due date: _____________________ |
| Are the Supervisor’s application and competency milestones realistic and resourced? | ☐ Yes ☐ No ☐ Revised target: _____________________________ |
| Has management reviewed the residual risks and approved the action plan? | ☐ Yes ☐ No ☐ Actions required: __________________________ |

# 12. Approval

| Function | Name | Signature | Date |
| --- | --- | --- | --- |
| Prepared by - Laboratory Manager / risk owner | ________________________ | ________________________ | ____________ |
| Reviewed by - QMS owner / Nominated Representative | ________________________ | ________________________ | ____________ |
| Approved by - CEO / top management | ________________________ | ________________________ | ____________ |

# Appendix A — Decision rules to prevent inappropriate report release

- Only a person whose SANAS approval covers the relevant scope may authorise reports as accredited.

- Internal delegation, seniority, industry experience, training completion or a planned SANAS assessment does not replace formal approval.

- If the sole approved TS is unavailable and no approved signatory arrangement is in place, affected reports remain on hold; preserve traceability and communication delays.

- If SANAS suspends or reduces accreditation, immediately apply the exact conditions and affected scope; do not use accreditation symbols or claims contrary to R 51-10 and applicable R 04 requirements.

- A CTS is not simply an external person asked to sign reports. It requires the formal process and controls described in SANAS R 03-10 clause 5.2.

- When in doubt about the effect of the personnel change on accreditation status or notification requirements, the CEO / Nominated Representative should seek written clarification from the relevant SANAS Accreditation Manager and retain the response.

# Source documents reviewed

- SANAS R 03-10, Nominated Representative and Signatories: Responsibilities, Qualifications and Approval, approved/implemented 4 March 2024.

- SANAS R 51-10, Suspensions, Reductions, Withdrawals, Expiry and Re-instatement of Accredited or GLP/GCP Compliant Organisations.

- ISO/IEC 17025:2017 — referenced as the laboratory’s management-system and technical competence standard; clause-level mapping should be checked against the laboratory’s-controlled copy and applicable SANAS documents.