# INTERNAL AUDIT PROGRAMME

Period Covered: November – December 2025
Standard: ISO/IEC 17025:2017
Approved by: Nonhlanhla Msibi
Next Review: February 2026

## 1. Objective

To verify that the laboratory’s management system and technical operations conform to ISO/IEC 17025:2017, internal policies, and regulatory requirements; and to ensure that the system is effectively implemented, maintained, and continually improved.

## 2. Scope

The audit covers all areas of the laboratory including:
• Management and documentation system
• Personnel competence and impartiality
• Facilities and environmental conditions
• Equipment and calibration
• Testing and method validation
• Sampling, data integrity, and reporting
• Risk management, corrective action, and improvement

ADDED (to address “Audit criteria not addressed”):
Audit Criteria:
Audits shall be conducted against the following criteria:
• ISO/IEC 17025:2017 requirements
• Laboratory Quality Manual and management system procedures
• Approved technical methods and work instructions
• Applicable regulatory, customer, and accreditation body requirements
• Risk management and corrective action procedures

## 3. Audit Team

| Role | Name | Competence / Area |
| --- | --- | --- |
| Lead Auditor |  | ISO 17025 systems / QMS |
| Technical Auditor |  | Technical methods / equipment |
| Observer (optional) |  | Trainee or support |

Note: Auditors are assigned to areas where they have no direct involvement to ensure impartiality.

## 4. Audit Schedule (November – December 2025)

| Week / Date | Audit Focus Area | ISO 17025 Clauses | Audit Scope & Key Activities | Responsible Auditor | Outputs / Records |
| --- | --- | --- | --- | --- | --- |
| Week 1: 10–14 Nov 2025 | Documentation, Quality Management & Control of Records | 8.1 – 8.3 | Review Quality Manual, objectives, policies, and control of documents. Verify review, approval, and version control processes. Check accessibility of controlled documents. Evaluate retention, protection, and disposal of records. | Lead Auditor | Audit checklist, NCRs, report |
| Week 2: 17–21 Nov 2025 | Personnel Competence, Training & Impartiality | 6.2, 4.1 | Review competence and authorization records. Check impartiality declarations and conflict-of-interest handling. Interview staff for awareness of QMS, methods, and confidentiality requirements. Evaluate training plans and effectiveness. | Lead Auditor / HR | Audit notes, interview forms |
| Week 3: 24–28 Nov 2025 | Facilities, Equipment & Environmental Conditions | 6.3 – 6.4 | Assess suitability and maintenance of lab facilities. Verify calibration, verification, and maintenance records. Review environmental control logs and calibration traceability. Observe equipment use and handling. | Technical Auditor | Equipment checklist, audit report |
| Week 4: 01–05 Dec 2025 | Testing, Method Validation & Measurement Traceability | 7.2 – 7.8 | Verify method validation, uncertainty, and verification records. Observe sample handling and testing workflow. Review traceability of standards and reference materials. Evaluate data integrity and calculation verification. | Technical Auditor | Observation sheets, NCR forms |
| Week 5: 08–12 Dec 2025 | Customer-related Activities, Reporting & Complaints Handling | 7.1 – 7.10 | Review contract reviews, quotations, and job acceptance forms. Evaluate client communication records and confidentiality handling. Verify test reports for accuracy, authorisation, and data transfer checks. Review complaint records and corrective actions taken. | Lead Auditor | Audit report, corrective action log |
| Week 6: 15–19 Dec 2025 | Risk Management, Corrective Action & Management Review Preparation | 8.5 – 8.9 | Review risk and opportunity register and updates. Evaluate recent corrective actions for root cause and effectiveness. Verify audit follow-ups and closure of NCRs. Review readiness for Management Review (inputs and outputs). | Quality Manager / Lead Auditor | Risk register, CAPA tracking, summary report |

## 5. Audit Methodology

• Planning: Each audit planned in advance with scope, criteria, and checklist.
• Execution: Evidence gathered through interviews, observation, and document review.
• Reporting: Findings documented and graded (Major NC, Minor NC, Observation, OFI).
• Follow-up: Corrective actions tracked and verified for effectiveness.

## 6. Reporting and Closure

Audit reports issued within 5 working days of completion. Corrective actions assigned to responsible personnel with deadlines. Effectiveness verified during the final week’s audit or next review. Summary findings presented at the next Management Review meeting.

ADDED (to address “No audit report submitted / results not demonstrated”):
• Audit results shall be formally communicated through an approved Audit Report.
• The Audit Report shall be distributed to relevant management and affected personnel within 12 working days after completion of the audit.
• Audit reports shall be submitted as objective evidence during internal reviews and external assessments.

ADDED (to address “No implementation date addressed”):
• Each nonconformity shall include an agreed implementation date for corrective action.
• Implementation dates shall be recorded on the NCR and corrective action tracking log.
• Delays to implementation shall be justified, documented, and approved by the Laboratory Manager or Operations Manager.

## 7. Audit Records

Records include:
• Annual audit programme
• Completed checklists and reports
• NCR forms and CAPA tracking sheet
• Attendance and meeting minutes
• Verification of corrective actions

ADDED (to address “No audit records referred to in procedure”):
• Audit records shall be maintained as controlled quality records in accordance with the document and record control procedure.
• Audit records shall provide objective evidence of audit planning, execution, findings, corrective actions, and effectiveness verification.
• Audit records shall be retained for a minimum period defined in the record control procedure and made available for internal and external audits.

## 8. Evidence of Systematic Coverage

This programme ensures full coverage of both management system (Clauses 8.1–8.9) and technical competence (Clauses 4–7) within the two-month period. It demonstrates that internal audits are planned, systematic, conducted by competent and impartial auditors, and used for continual improvement.

## Annex A: Internal Audit Checklist Template

| Clause | Requirement | Objective Evidence | Findings / Comments | NC / OFI |
| --- | --- | --- | --- | --- |

This template is used during each audit activity to record evidence and findings against the relevant ISO 17025 clauses.