## Summary
PROFICIENCY TESTING SCHEME PLAN
| Document number |  | Revision | Pages
| ASMF 7.2.1.3 |  | 0 | 2
| Compiled by: |  | Laboratory Manager
| Authorised by: |  | Operations Manager
SUMMARY OF ACTIVITIES
Activities |  |  | Comments
Create application form to join the scheme | AS002PT form implemented, | effective date 04/2025 | Send to participants, immediately when markerting the scheme + issue samples R0
| AS001FD pricelist implemented | effective date 04/2025
Create necessary subscriptions | Sage, LIMS | effective date 05/2025
| Target date | Comments
Search for workshop | 2025-03-31 | Rent workshop, contract signed with API Agency
Set up communication lines | 2025-04-30 | IBC practice set up domain for emails, letter head, profile and website
Delivery of Equipment, furniture & tools | 2025-04-30 | Basic coal analysis equipment
Recruit personnel - head hunt | 2025-04-30 | Mpho Serage and Sifiso Nyambi
Recruit analyst & oprators | 2025-04-30 | Signed an SLA with Hlogirati, four analyts (students in training obtained
Set up communication lines | 2025-04-30 | IBC practice set up domain for emails, letter head, profile and website
Start documenting procedures, checklist, policies, method validations, etc | 2025-10-30 | In progress and continuously improving
Source coal | 2025-04-30 | Collected coal from Elandsfontein
Perform medicals purchased PPE | 2025-05-31 | All personnel including MD received certificates of fitness
First PT sample prepared and distributed (pulp) | 2025-05-31 | First PT scheme running, samples were issued for R0 + plus introduction of the business
Appointed a consultant to draft a report (Hlomi) | 2025-05-31 | Reports were issued First week of June 2025
Plan to issue two PT samples (A & B)- pulps | 2025-07-31 | First week of July, execution done
Create CRM catalogue | 2025-08-31
Start markerting the catalogue + increase PT participation | 2025-08-31 | Continuously
Plan to issue HGI PT sample | 2025-10-31
Plan to issue AI and semi-prepared moisture | 2025-11-30

## Plan
List of activities
| Activities | Target date | Comments
1 | Search for workshop | 2025-03-31 | Rent workshop, contract signed with API Agency
2 | Set up communication lines | 2025-04-30 | IBC practice set up domain for emails, letter head, profile and website
3 | Delivery of Equipment, furniture & tools | 2025-04-30 | Basic coal analysis equipment
4 | Recruit personnel - head hunt | 2025-04-30 | Mpho Serage and Sifiso Nyambi
5 | Recruit analyst & oprators | 2025-04-30 | Signed an SLA with Hlogirati, four analyts (students in training obtained
6 | Set up communication lines | 2025-04-30 | IBC practice set up domain for emails, letter head, profile and website
7 | Start documenting procedures, checklist, policies, etc | 2025-10-30 | In progress
8 | Source coal | 2025-04-30 | Collected coal from Elandsfontein
9 | Perform medicals purchased PPE | 2025-05-31 | All personnel including MD received certificates of fitness
10 | First PT sample prepared and distributed (pulp) | 2025-05-31 | First PT scheme running, samples were issued for R0 + plus introduction of the business
11 | Appointed a consultant to draft a report (Hlomi) | 2025-05-31 | Reports were issued First week of June 2025
12 | Plan to issue two PT samples (A & B)- pulps | 2025-07-31 | First week of July, execution done
13 | Create CRM catalogue | 2025-08-31
14 | Start markerting the catalogue + increase PT participation | 2025-08-31 | Continuously