## Sheet1
NC No. | Date Identified | Detected By (Name / Dept.) |  | Description of Non-Conformity (What went wrong?) | Reference Document / Procedure / Clause | Immediate Action Taken (Correction) | Impact Assessment (Risk to PT / RM validity?) | Root Cause Analysis (Why it happened) | Corrective Action Plan (Prevent recurrence) | Responsible Person | Target Completion Date | Date Completed | Effectiveness Verification (Outcome) | Verified By (Name & Date) | Status (Open / Closed)
NC01 09/2025 | 05/09/2025 | Tshepo Maponya | 1 | CRM's of two different qualities were packaged and labelled as one sample CRM 006 and PT A Aug 2025. | ISO 17034, Clause 7.5. | Isolate the affected CRM batches and remove them from storage. | Major NC, directly affects the validity of results. | *Inadequate planning for future in that at the time of packaging, stickers were unavailable. *Cross contamination due to incorrect storage/handling | Purchase stickers ahead of time to avoid storing samples without labels. Also thouroughly label the storage compartments to make identifying samples/batches easy. | Laboratory Manager | 06/09/2025 | 05/09/2025 | effective | Operations Manager | Closed
NC02 09/2025 | 15/09/2025 | Operation Manager | 1 | Reference values & their establishment omitted within all PT reports (1-6). | SANAS R80-06 Clause 7.3. | Add a section for CRM characterisation and their establishment on the PT final report. | Does not directly affect the validity of results. The lab did have in place a document that explains how assigned values are derived from the PT result, it just failed to include it within the PT reports. | Oversight when doing the checklist requirements of a PT report (see report for details). | The section has been integrated into the template for the final PT reports. | Laboratory Manager | 17/09/2025 | 15/09/2025 | effective | Laboratory Manager | Closed
NC03/2025 T | 05/01/2026 | SANAS | 1 | Stability monitoring results for CRM004 and CRM 005 (July-Dec 2025) were incorrectly assigned due to swapping of CRM bottles during storage | ISO 17034, Clause 7.11. | CRM preparation and packaging procedure was revised to mandate immediate individual bottle labelling during packaging and to prohibit CRM units storage/testing unless permanent identification labels are available amd applied. A formal hold or quarantine process including approved temp identification was introduced for such situations where labels are unavailable. | Major NC, directly affects the validity of results. Although the batches were verified to be in their respective stations in the storage room, the swap could've led to catastrophic results | * CRM stickers not available at the time of packaging. * No secondary/temporary labelling system defined for use during stickers shortage *Packaging procedure allows packaging to proceed when CRM stickers | Buy stickers ahead of time and/or implement the processes updated on the working instruction. | Laboratory Manager | 07/01/2026 | 06/01/2026 |  |  | Open (Check ~march)
NC04/2026 T | 15/01/2026 | Operation Manager | 1 | No records for 4.75mm crusher efficiency | ISO 17025 7.5.1 | Update the ASIW001 document to include when to do the efficiency of the crusher in question. | Minor. The crusher was verified for effeiciency before use, however not documented. | The procedure lacked explicit instruction on the crusher effeiciency of 4.75mm. Thus, efficiency was done unofficially. | Update the procedure to explicitly state to do the efficiency of 3 and 4.75 mm crusher prior to use. Also release a memo to make personnel aware of the change. | Laboratory Supervisor | 17/01/2026 | 16/01/2026 | Effective | Laboratory Manager | Closed
| 15/01/2026 | Operation Manager | 1 | No records for in-house maintenance of equipment | ISO 17025 7.5.1 | Purchase an in-house maintenance book | Minor. Minor maintenances were done on equipment but not logged. Only records for major maintenances from services provider are present. | Initially, the lab did not see the need to have an in-house given that service providers leave job cards after major maintenances. | Buy a book. | Laboratory Supervisor | 15/01/2026 | 15/01/2026 | Effective | Laboratory Manager | Closed
NC06/2026 T | 05/02/2026 | SANAS | 1 | CAB claimed conformity/accreditation to ISO/IEC 17025 even though it is still going through the accreditation process | ISO 17025(SANAS F48 cl 5.3) | Revise the document to make it clear about the position of the lab's non accredited status. | Major. It is prohibited for the lab to mispresent itself with regards to accreditation status. | The lab did not intend to claim conformity/accreditation. CAB only meant that the QMS is designed based on the structure of ISO 17025. | Update doc ASMF5.3 rev 00 to clearly state that the lab is not accredited but rather in the process to get accreditation. | Laboratory Manager | 10/02/2026 | 09/02/2025 | Effective | Laboratory Manager | Closed
NC07/2026 T | 02/09/2026 | SANAS | 1 | The requirements of the standard, customer regulatory authorities and organization providing regulation was not addressed/documented in the QMS of the CAB | ISO 17025 (SANAS 5.4 F48-07) | The drafting of the requirements of standards, customer, reg auth etc (ASMF5.4) was done | Major | The QMS was still being developed therefore the document that states the requirement of standards, customers, regulatory authorities was not drafted leading to an incomplete system documentation | The drafting of the requirements of standards, customer, reg auth etc (ASMF5.4) was done | Laboratory Manager | 09/02/2026 | 09/02/2026 | Effective | Laboratory Manager | Closed
NC08/2026 T | 04/02/2026 | Sifiso Nyambi | 1 | The subcontractor/coutractor register doesn't list any supplier/service provider. Another point that was not addressed: how does the lifted evaluation criteria for supplies or services help in assessing their performance. | ISO 17025 (SANAS 6.6.2 F48-07) | The updated list for evaulation was created | Major | Oversight and human error were the root cause through the use of cause tool | The updated list for evaulation was created | Operations Manager | 04/02/2026 | 06/02/2026 | To be checked after SANAS assessment | Laboratory Manager | Closed
NC09/2026 T | 02/09/2026 | SANAS | 1 | Cab did not outline how it intends to make the complaint handling process avaliable to interested parties and how it plans to issue communication of the final outcome of logged complaints | ISO 17025 (SANAS F48 Cl7.9.2) & 7.9.7 | The complaint and appeal procedure document (ASMF 7.18B) was updated to include the information already published on the website | Minor | The issue was caused by oversight and incomplete system documentation. Although the complaint and appeal handling information was avaliable on the company website, it was not fully captured in the formal complaint and appeal procedure document | The complaint and appeal procedure document (ASMF 7.18B) was updated to include the information already published on the website | Laboratory Manager | 09/02/2026 | 09/02/2026 | Effective | Laboratory Manager | Closed
NC10/2026 T | 02/09/2026 | SANAS | 1 | The responsibility for authorising the resumption of work not clearly defined in 7.17 document | ISO 17025 (SANAS F48-07 Cl7.10) | The drafting or updating of the document (ASMF7.17) clearly stating that the operations/ lab manager authorizes resumption of work | Major | Due to incomplete system documentation, nowhere in the documented system was it clearly stated as to who gives authority for resumption of work | The drafting or updating of the document (ASMF7.17) clearly stating that the operations/ lab manager authorizes resumption of work | Laboratory Manager | 02/09/2026 | 02/09/2026 | Effective | Laboratory Manager | Closed
| 10/02/2026 | SANAS | 1 | The sampled procedure for the determination of inherent moisture AS0041W has no date (effective and next review date) | 7.2.1.2 | The document AS0041W was updated with the effective date and next review date | Major | This matter was an oversight and as a result, there was no effective and next review date for the sampled procedure for determination of inherent moisture AS0041W | The document AS0041W was updated with the effective date and next review date | Laboratory Supervisor | 10/02/2026 | 10/02/2026 | Effective | Laboratory Manager | Closed
NC12/2026 | 10/02/2026 | SANAS | 1 | it was noted that there is no additional process/procedure detailinng the implementation of the requirement 6.4 | 6.4 | A new document was drafted -ASMF6.3 PROC - detailing the additional processes of the implementation of 6.4 requirement and memo-003 was sent out to all personnel | Major | The required process for clause 6.4 were not fully written down. The root cause was incomplete system documentation | A new document was drafted -ASMF6.3 PROC - detailing the additional processes of the implementation of 6.4 requirement and memo-003 was sent out to all personnel | Laboratory Supervisor | 11/02/2026 | 11/02/2026 | Effective | Laboratory Manager | Closed
NC13/2026 | 06/02/2026 | SANAS | 1 | The timelines to address NCs was not specified | ISO 17025 (Clause 8.7.1, SANAS F48-07) | Document ASMF7.17 was updated with specified timesframes for closing/addressing NCs | Major | Incomplete system documentation | Document ASMF7.17 was updated with specified timesframes for closing/addressing NCs | Laboratory Manager | 06/02/2026 | 06/02/2026 | Effective | Laboratory Manager | Closed
NC14/2026 | 12/02/2026 | SANAS | 1 | There is no clear indication of contributors to measurement uncertainty UB001 only indicates expanded uncertainty, no contributors mentioned. | ISO 17025 (Clause 7.6) | Revised UB001 to include detailed uncertainty budget tables for volatile matter, inherent moisture, ash determination and calorific value. | Major | Oversight | UB001 was revised to include uncertainty budget table for Vol matter, IM, Q-Ash and CV. | Laboratory supervisor | 12/02/2026 | 12/02/2026 | To be checked after SANAS assessment |  | Closed
NC15/2026 | 11/02/2026 | SANAS | 1 | Procedure for the control of NC's doesn't adequately define how the effectiveness of corrective actions is reviewed and verified. Timeliness for effectiveness review not specified, particularly where immediate verifcation is not practical, and no distinction is made b/w minor and major NCS. Procedure doesn't clearly require changes to the management system where necessary to prevent recurrence. In addition, corrective actions, records, including root causes, actions taken, and results of effectiveness verificationare not explicitly required to be retained. This limit's the lab's ability to demonstrate that corrective actions are effective and sustained. | ISO 17025 (SANAS F48 cl 8.7) | Management of NC procedure (ASMF 7.17) was updated to include the omitted requirements. | Major | Incomplete system documentation & processes not defined. The procedure for NC working failed to adress how the corrective action effectiveness are revised/verifed detail requirements for changes in management system as well as record retention. | The Management of non-conforming work (ASMF 7.17) was updated to include the omitted requirements | Laboratory Manager/Supervisor | 11/02/2026 | 12/02/2026 | To be checked after SANAS assessment |  | Closed
NC16/2026 | 06/02/2026 | SANAS | 1 | Not all performance charatcers were evaluated in the report AS003MV, and no valid reason provided. | ISO 17025 cl 7.2.2 | Update AS003MV procedure to include reasons for omission of certain perfomance characteristics. | Major | Original validation report focused on the parameters making the method sufficiently fit for purpose, but neglected to include reasons for omission. Thus, making the NC to be classified as incomplete system documentation. | Update AS003MV procedure to include reasons for omission of certain perfomance characteristics. | Operations/Laboratory Manager and Lab Supervisor | 06/02/2026 | 06/02/2026 | To be checked after SANAS assessment |  | Closed
NC17/2026 | 11/02/2026 | SANAS | 1 | Internal audit program lacked clarity and completeness in several key areas. Audit criteria are not explicitly defined as required by ISO 17025, and there is limited documented evidence of formal reporting to management. Corrective actions arising from audits not assigned not assigned, implementation timelines, and audit retention is nit clearly specified. | ISO 17025 (SANAS F48-07 Cl 8.8) | Update internal audit AUI001 | Major | Incomplete system documentation | Always visit AUI001 just before a major internal audit | Laboratory Manager/Supervisor | 11/02/2026 | 11/02/2026 | Next audit date |  | Closed
NC18/2026 | 05/02/2026 | Internal Observation | 1 | Organization lacked a process/procedure for selection, appointing, and recruitment of technical personnel. | ISO 17043 6.2. | Document a procedure for the selection and recruitment of technical personnel | Major | Incomplete system documentation | All technical personnel must be recruited in accordance to the organisation's requirements (e.g., qualification and experience etc.) | Operations Manager/ HR | 05/02/2026 | 05/02/2026 | (To be checked after in-take of new employees) |  | CLosed
NC19/2026 | 06/02/2025 | SANAS | 1 | Competency declaration ASMI 6.1. Rev 00 for technical tasks only, not indicating the overall responsibility to be able to evaluate significance of deviations. | ISO 17043 6.2.3. | Revise form ASMF6.1. toincludea section explaining that personnel have been trained to identify deviations, assess, investigate and address NCs. | Major | Incomplete system documentation | Train personnel from the get go to identify, assess, and investigate deviations. | Laboratory Manager/Supervisor | 06/02/2026 | 06/02/2026 | 2026 May |  | Closed
NC20/2026
NC21/2026 | 12/02/2026 | Internal Audit | 1 | On the 29/09/2025 samples were analysed with the control sample out of limits for CV. | ISO 17025 cl 7.7 | Re-train the personnel and check if any PT samples were affected. | Major | Negligence | Re-train Lilo Photo | Laboratory Supervisor | 13/02/2026 | 13/02/2026 | 16/04/2025 (Next check date) |  | Closed
NC22/2026 | 07/04/2026 | N. Chiliza | 1 | At the time of assessment both the vessel and lid were placed in the oven contrary to procedure AS004IW where only open vessel should go to the oven and the lid into the desiccator. | ISO 17025 cl 7.2 | A memorandum was sent out | Major | Negligence | Personnel was reminded of the proper way to carry out IM analysis. | Laboratory Manager/Supervisor |  | 09/04/2026
NC23
NC24
NC25
NC26
NC27
NC28
NC29
NC30
Number of NCs: |  |  | 21